## Sheet1
Lofthus frukt og saft
Assigned to | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
| 2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28 | 2019-03-01 | 2019-03-04 | 2019-03-05 | 2019-03-06 | 2019-03-07 | 2019-03-08 | 2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22
Project manager | Project management, customer contact |  |  |  |  | Project management, customer contact |  |  |  |  | Project management, customer contact |  |  |  |  | Project management, customer contact
Project manager, Front-end developer, Photographer, Content writer | Initial meeting with customer
Project manager, Front-end developer, Content writer | Needs assessment, project planning | [8 empty] | Halfway meeting with customer, presentation of plans and direction
Content writer, Front-end developer |  | Site structure and outline
Content writer |  |  | Content planning and research |  |  | Content creation and formatting
Front-end developer |  |  | Style tiles, iconography |  | Wireframing | UI Planning and testing |  | Website creation, coding and basic styling |  |  | Website creation, coding and basic styling | Styling website, responsive design |  |  |  | Browser and device testing |  | Validating
Front-end developer | [18 empty] | Polish and final touches
Photographer | [5 empty] | Products photoshoot |  | Employee, factory and offices photoshoot |  |  | Preparing images for use on web
Project manager, Front-end developer, Photographer, Content writer | [19 empty] | Site launch